## Slide 1
Upgrade and consolidation of post‑trade infrastructure in Ukraine
Implementation plan (jointly developed by NSSMC, NDU, NBU and the Settlement Center with consultation from EBRD and Oliver Wyman)
Stakeholder Workshop #3
31 May 2017

## Slide 2: Objectives of today’s meeting
Jointly recap the target set-up
Provide update on overall progress since last workshop (NSSMC)
Present and align on detailed implementation plans developed by four institutions with consultation from EBRD and Oliver Wyman (work block leads)
Discuss next steps

## Slide 3
Recap: Target set-up
1

## Slide 4: Oliver Wyman recommends to follow a clean-slate approach for the clearing layer implementation

## Slide 5: Funding of the transformation and long term development should be provided by a revised ownership structure with strategic interests

## Slide 6
Implementation plan overview
2

## Slide 7: For the transformation program, four major work blocks were identified
Work block | Activities
Transformation ramp-up | Transition: stakeholder buy-in, program governance, handover
A. Post trade corporate finance, governance & organisation | Corporate Finance: Financial plan, investor acquisition, negotiation with exchanges, ownership structure
 | Governance & top level organisation: Post trade holding governance and leadership
B. Light CCP operating model implementation | Concept specification: System requirements, detailing of outlined target concept
 | IT: Vendor selection process (see CSD IT)
 | Operations & processes: Risk management processes, workflow determination
 | Organisational set-up: Teams, positions, roles & responsibilities
 | Pricing
 | Risk analysis & IT: Clearing engine and risk models, algorithms, implementation
C. Integrated CSD operating model implementation | IT: Vendor selection process, implementation of new platform, testing and refinement
 | Operations & processes: Business process analysis / optimisation / process documentation
 | Organisational set-up: Teams, positions, roles & responsibilities
 | Pricing
 | Transfer of assets onto new platform
D. Implementation support | HR: FTE / capability mapping, gap and overlap identification, recruiting, lay-offs
 | Communication: Participant information, official market communication

## Slide 8: Overall transformation is expected to take 18-21 months with a go-live of the new post trade set-up in 01/2019
Implementation of new ownership structure
Phase C
Work blocks |  | 
 | Transformation program ramp-up | 
A | Post trade corporate finance, governance & organisation | 
B | Light CCP operating model implementation | 
C | Integrated CSD operating model implementation | 
D | Implementation support | 
2017
2018
2019
Impl. prep.
Program kick-off
Fin. plan
Investor acquisition
Pricing
Org. set-up
Official market Communication
Transfer of assets, start with NDU then gov. bonds from NBU
Con- cept
Go-live of new integrated CSD
Pricing
Transformation completed
Org. set-up
Transformation board meetings
monthly progress reports
Concept specification
Negotiation with exchanges
Operations & processes
Completion/ major milestone
Dependencies
Testing and refinement
Go-live of light CCP
Holding govern. & top level org.
Operations & processes
Risk analysis and IT , incl. im- plementation (linked with CSD IT)
Ownership structure
Post trade governance finalised
HR: FTE / capability mapping, gap and overlap identification, recruiting, lay-offs
New organisation fully staffed
Participant information
IT: implementation of platform
IT: vendor selection process
IT: vendor selection process (see CSD IT)
Testing and refinement
Updated in May 2017, based on feedback from work block leads
New ownership structure implemented

## Slide 9: A Transformation Board should be introduced to maintain oversight, and coordinate with the program lead who drives the overall progress
Transformation Board
PMO
Program lead
  Decision-making body on project related topics
  Review and confirmation of project results
  Control over the overall program
  Coordination of work blocks
  Process-related support of the program and project managers and develop-ment of program structures and plans
  Scope management and “gate-keeping“
  Temporary set-up support / start-up grant
  Production of project results, decision memos, presentations and documentation
A
B
C
D
Description
Proposed transformation program governance
Implementation support
  Development of project results
  Responsibility for the projects and fulfilment of the project goals and milestones
Integrated CSD operating model implementation
Light CCP operating model implementation
Post trade corporate finance, governance & organisation
- Local stakeholders and major investors-
- Tbd -
Dmytro Tarabakin (Max Libanov)
Mindaugas Bakas (Yuriy Shapoval, Iryna Gnatyuk, Andriy Suprun, Mykola Selekhman, Alla Papaika)
Yuriy Shapoval (Mindaugas Bakas, Iryna Kurochkina, Mykola Selekhman)
Mindaugas Bakas (Andriy Suprun, Yuriy Shapoval, Iryna Gnatyuk, Iryna Omelchenko)
Set-up = Lead (Team)

## Slide 10
Detailed work block plans
3
Updated in May 2017, based on feedback from work block leads

## Slide 11: Block A: Post trade corporate finance, governance & organisation (1/2) Detailed timeline
A | B | C | D
 |  |  | 2017 |  |  |  |  |  |  |  |  |  |  |  | 2018 |  |  |  |  |  |  |  |  |  |  |  | 2019 |  |  |  |  | 
 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  | 
Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1 | Corporate Finance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Financial plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Investor acquisition |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Negotiation with exchanges |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | Holding governance and top level organisation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Key meetings/ workshops |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Governance and leadership workshop |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Key milestones |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Light CCP impl. approach determined |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Holding governance determined |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Ownership structure defined |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | New ownership structure implemented |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Updated in May 2017, based on feedback from work block leads

## Slide 12: Post trade corporate finance, governance & organisation (2/2) Key activities, dependencies and risks
Activity
Description
Responsibilities
Corporate Finance
1
Development of financial plan – use conservative assumptions
Required investments
Operational cash-flow from core business (revenues / costs)
Projections for future profitability
Pay-back period / break even
Holding governance and top level organisation
2
Develop governance principles for holding
Determine positions and potential composition of leadership roles in future post trade entities
Finalise and agree with new shareholders in a dedicated workshop
Mindaugas
Yuriy
Dmytro
Andriy
Acquisition of investors, based on financial plan
Investment from Ministry of Finance
Pitch to strategic investors (domestic & international)
Dmytro
Mindaugas
Yuriy
Negotiation with exchanges
Clearing mandate for the Ukrainian market
Implications on shareholder structure
A | B | C | D
Real Estate @ RC
Forecasting future business
Dependencies & risks
Limitations in legislation to change ownership
Dependent on Financial Plan
Dependent on parallel EBRD project and Financial plan
Political decision from shareholders and other stakeholders
Dmytro
Alla
Mindaugas
Andriy
Updated in May 2017, based on feedback from work block leads

## Slide 13: Comments to block A
Financial plan
  Forecasting while expecting dramatic changes in business model and environment for CCP and CSD is extremely complicated and result can be easily challenged by potential investors
  Real estate that makes large part of CCP capital has to be removed form balance eventually, though this process can run in parallel and should not implicate the overall reorganization
    The process of real estate removal should be reflected within financial plan to provide investors with sufficient information
Investor acquisition
  Extension of allocated time until second half of 2018: Current laws prescribe the limitations to the ownership structure of CSD and CCP. Real negotiations on investor acquisition can be resumed after laws are passed or passed first hearing (?)
Ownership model
  The final model of holding depends on political decisions on the level of Commission, NBU, Ministry of Finance, other
    This will take many meetings and discussions, thus it will take a lot more time than a month
  Actual implementation of new ownership structure will be possible only after the changes in the regulation, i.e. not earlier than end of 2018
Updated in May 2017, based on feedback from work block leads
A | B | C | D

## Slide 14: Light CCP operating model implementation (1/3) Detailed timeline
 |  |  | 2017 |  |  |  |  |  |  |  |  |  |  |  | 2018 |  |  |  |  |  |  |  |  |  |  |  | 2019 |  |  |  |  | 
 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  | 
Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1 | Concept specification |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | IT: Vendor selection (see CSD IT) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3 | Operations & processes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4 | Organizational set-up |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
5 | Pricing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
6 | Risk analysis and IT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Risk calculation logic for Ukraine |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | IT implementation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
7 | Testing and refinement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Key meetings/ workshops |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Vendor selection workshop |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Workshops with vendor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Key milestones |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Light CCP impl. approach determined |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | UA-specific clearing module impl. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Go-live of light CCP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
A | B | C | D

## Slide 15: Light CCP operating model implementation (2/3) Key activities, dependencies and risks
Concept specification
1
Translate target concept into system requirements (for integration in CSD RfP, or separate RfP)
Elaborate on detailed technical questions (e.g. own funds of CCP to be ring fenced in default waterfall)
Operations & processes
3
Determine clearing and risk management operations
Define processes including documentation
Determine Service Level Agreements
Organizational
set-up
4
Derive required number of FTE to perform operations
Design organisational set-up based on core activities, taking spans & layers considerations into account
Tbd (ideally on name basis)
Activity
Description
Pricing
5
Develop principles for light CCP pricing
Derive light CCP pricing schedule so that clearing core business can be self sufficient
Tbd
IT: Vendor selection
2
See CSD IT vendor selection for integrated solution
Alternatively, run separate RfP process and select vendor
Tbd (ideally on name basis)
A | B | C | D
Responsibilities
Tbd
Dependencies & risks
Tbd
Tbd
Tbd
Tbd

## Slide 16: Light CCP operating model implementation (3/3) Key activities, dependencies and risks
Activity
Description
Tbd
Risk analysis and IT
6
Determine risk calculation logic for Ukraine, incl. risk parameters, confidence levels, potential liquidity surcharges, liquidity threshold for light CCP clearing vs. pre-funding etc.
Implement Clearing System and link with CSD and exchanges
Adopt risk calculation logic for Ukraine
Testing/ refinement
7
Test the functionality of the clearing engine and risk calculation
Identify system errors/ bugs and refine accordingly for go-live
A | B | C | D
Responsibilities
Tbd
Dependencies & risks
Tbd
Tbd

## Slide 17: Integrated CSD operating model implementation (1/3) Detailed timeline
 |  |  | 2017 |  |  |  |  |  |  |  |  |  |  |  | 2018 |  |  |  |  |  |  |  |  |  |  |  | 2019 |  |  |  |  | 
 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  | 
Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1 | Operations & processes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | Organizational set-up |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3 | Pricing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4 | IT: Vendor selection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
5 | IT: Implementation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Business requirements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Platform set-up |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
6 | Testing and refinement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
7 | Asset transfer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Key meetings/ workshops |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Vendor pitches / selection workshop |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Workshops with selected vendor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Key milestones |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Vendor selected |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Go-live of new system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
A | B | C | D
Updated in May 2017, based on feedback from work block leads

## Slide 18: Integrated CSD operating model implementation (2/3) Key activities, dependencies and risks
Operations &
Processes
Analyse existing processes and weak points
Optimise operations and processes including documentation of process maps
Determine Service Level Agreements
Organizational
set-up
Derive required number of FTE to perform operations
Design organisational set-up based on core activities, taking spans & layers considerations into account
IT: Implementation
Finalize Request for Proposal
Run vendor selection process incl. evaluation of offers
Select vendor/partner and IT system for new CSD
Mindaugas
Yuriy
Mykola
Andriy
Pricing
Develop principles for CSD pricing
Derive new CSD pricing schedule so that CSD core business can be self sufficient
1
2
3
5
Mindaugas
Yuriy
Mykola
Andriy
IT: Vendor selection
4
Together with vendor, jointly develop detailed business and IT infrastructure requirements for potential tailoring needs
Implement tailored solution incl. links to light CCP, NBU payment system etc.
Activity
Description
A | B | C | D
Responsibilities
Requires principles of access to Payment System
Requires principles of new legal framework
Requires CCP processes analysis
Dependencies & risks
Depends on IT solution, potential STP level and changing business environment
Depends on IT solution, potential STP level and changing business environment
Financing structure
Requires at least high-level processes description document with approval from all stakeholders
Requires principles of access to Payment System
Requires principles of new legal framework
Requires CCP processes analysis
Might require investments into IT infrastructure
Updated in May 2017, based on feedback from work block leads

## Slide 19: Integrated CSD operating model implementation (3/3) Key activities, dependencies and risks
Testing and
refinement
Test the functionality of the new platform
Identify system errors/ bugs and refine accordingly for go-live
6
Mindaugas
Yuriy
Mykola
Andriy
Asset transfer
Transfer NDU assets on new platform & shut down current system
Transfer NBU assets on new platform (potentially after successful test phase with NDU assets) & shut down current system
7
Mindaugas
Mykola
Andriy
Activity
Description
A | B | C | D
Responsibilities
Requires clear business process description
Language barrier
Dependencies & risks
Preparation for data migration will have to be started well in advance
Updated in May 2017, based on feedback from work block leads

## Slide 20: Comments to Block C
Operations processes description is the key document for building the new infrastructure
  Must contain the expected new business process structure to prioritize automation of crucial and manual labour intensive processes
  Must be in line with projected legal changes
  Will be the basis for configuring the IT systems (CSD core system, messaging, reporting, billing, etc.)
  Without agreement on basic principles of key processes, the IT Vendor selection cannot be finalized
  Finalization of key processes description might take more time
IT tasks have been shifted earlier, as some processes like building the test environment can be started without finalization of processes documentation
  On the same time, it imposes risk of additional customization in later stages of the project
Vendor selection process must also cover the requirements for IT infrastructure on CSD and CCP side
Updated in May 2017, based on feedback from work block leads
A | B | C | D

## Slide 21: Implementation support (1/2) Detailed timeline
 |  |  | 2017 |  |  |  |  |  |  |  |  |  |  |  | 2018 |  |  |  |  |  |  |  |  |  |  |  | 2019 |  |  |  |  | 
 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  | 
Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1 | HR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Description of roles |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Identification of gaps and overlaps |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Hiring of new staff / lay-offs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | Communication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Participant information |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Official market communication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Key meetings/ workshops |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | HR workshop |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Interviews with candidates |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Key milestones |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Go-live of new set-up |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
A | B | C | D

## Slide 22: Implementation support (2/2) Key activities, dependencies and risks
Activity
Description
A | B | C | D
HR
Derive required capabilities for the light CCP as well as the integrated CSD
Define roles and responsibilities including comprehensive job descriptions
Communication
Participant information
Information of post trade participants about planned transformation
Discussion of implications
Tbd (ideally on name basis)
1
2
Conduct gap analysis
  Identify staff overlaps and capability gaps in current FTE base
  Allocate existing staff to new roles (where possible) and prepare lay-offs
Tbd (ideally on name basis)
Advertise open jobs
Run recruiting process
  Screening, interviews, negotiations etc.
  Contracting
Official market communication
Prepare market communication program
Inform CSD and Clearing members before public disclosure
Official market communication about changes in post trade set-up
Responsibilities
Tbd
Dependencies & risks
Tbd
Tbd
Tbd
Tbd

## Slide 23
Next steps
4

## Slide 24: Next steps
Program lead to keep overall momentum and provide guidance / steering to work blocks as necessary (incl. regular check-ins with work block leads)
PMO to set up the overarching process and determine requirements
  Set-up of monthly transformation board meetings
  Format of status updates / templates
  Etc.
Dedicated kick-off sessions for each work block (work blocks A-C in particular)
  Organised by work blocks leads
  Ramp-up of additional resources
  Agreement on modus operandi